## Weighted Scoring Model
Weighted Decision Matrix for Mercy Health Management
| Created by: Nivedita Hari | Date: 09/29/17
| Criteria | Weight | Recreation & Wellness Project | Health Coverage Costs Model | Cross-selling System | Web-enhanced communication System
Evaluate the four projects listed above by preparing a weighted scoring model using the template provided. Develop at least four criteria, assign weights to each criterion, assign scores, and then calculate the weighted scores. Submit the spreadsheet and bar chart with the results. Include a description of the weighted scoring model and the results. | Strategic Fit | 25% | 75 | 55 | 78 | 86
| Adherence to key goals | 15% | 78 | 74 | 81 | 91
| Investment to implement | 10% | 63 | 66 | 19 | 8
| Employee friendly | 10% | 82 | 48 | 0 | 0
| Customer centric | 10% | 0 | 0 | 92 | 75
| Feasibility | 25% | 77 | 29 | 55 | 18
| ROI of 10% plus | 5% | 23 | 68 | 10 | 22
| Weighted Project Scores | 100% | 65.35 | 46.9 | 57 | 49.05
Description on next tab

## Description
Evaluate the four projects listed above by preparing a weighted scoring model using the template provided. Develop at least four criteria, assign weights to each criterion, assign scores, and then calculate the weighted scores. Submit the spreadsheet and bar chart with the results. Include a description of the weighted scoring model and the results.
Analysis of projects at Mercy Health Management
Recreation and Wellness Project | The project seems to be a good fit for the company's strategic goal of saving internal costs. It targets health insurance premiums of employees and takes initiatives to reduce them, there by adhering to key goal of saving company's money in the long run. As an initial investment, health care memberships, health care equipment and instructors are required besides the web application in which employees can enroll themselves into health activities. I looks very promising from employee's POV and provides no benefit to the customers. This project looks feasible and can be completed in a short duration. It gives an ROI of 14% by saving the insurance premiums of current employees to $30 per year. This is the most promising project of all the showcased projects at Mercy Health Management.
Health Coverage Costs Model | This project is looks employee friendly, although employee has very little to do in this approach. The costs are estimated to diminish once the employee enters his data into the new web system regarding his health care expenses. There is no customer value to this project as this is internal to the company. The project does not look feasible because it is highly dependent on employee's credibility of input of correct data on his behalf which may generate incorrect results. The ROI on the project is good and it sticks to the company's goal of and strategy of reducing internal costs.
Cross-Selling System | This system aims at increasing the cross-selling of products among the customers. The approach fits the strategy and goal by offering discounts to customers on multiple purchases. However, there is a huge investment involved and thus in not preferred. Even though this is highly customer centric, as the ROI is way less than 10% and there is no employee involvement in this initiative.
Web-Enhanced Communication System | This project implements one of the key goals of the organization to improve communication between the customers, suppliers, vendors etc. Again, as in the cross-selling system, there is a huge investment and ROI is very less. The maintanence costs are also atleast 20% of the development costs each year. The approach is customer friendly but looks confusing when feasibility is concerned. Needs more inputs and information to be considered as future projects.